# PROJECT UNDERSTANDING & BACKGROUND

Hardesty & Hanover (H&H) is a specialty engineering firm focused on movable bridges. The firm has been in continuous practice since 1887 and currently has the largest staff of engineers in the United States dedicated to movable bridge design, rehabilitation, and inspection. H&H has performed work on movable bridges across the U.S., Canada, the U.K., and Ireland, including bascule, vertical lift, swing, and rolling bascule structures.

Alameda County Public Works Agency is seeking to rehabilitate the existing bridge deck of the iconic Miller-Sweeney Bridge at Fruitvale Avenue over the Oakland Estuary, between Alameda Avenue and Blanding Avenue. The structure is a four-lane single leaf bascule, approximately 215 feet in total length, with a 98-foot movable span over a navigable waterway connecting to the San Francisco Bay. The curb-to-curb roadway width is about 52 feet, carrying two 13-foot lanes in each direction, with protected sidewalks approximately 6 feet wide on each side for pedestrian traffic. Vertical clearance over the waterway is approximately 15 feet at high tide and 21 feet at low tide. The bridge was constructed by the U.S. Army Corps of Engineers, opened to the public on December 12, 1973, turned over to the County in 1975, and named Miller-Sweeney. It carries roughly 28,000 vehicles per working day, so keeping it operable during construction is a hard constraint.

The proposed scope of work is similar to three projects H&H has completed within the last year, and the firm already knows this bridge from prior in-depth M&E inspections and from a remote-control operation study performed for the County. In the last twelve months, H&H has completed deck rehab, structural repairs, and rebalancing work on the Broadway Bridge in Portland, OR, the MLK Jr. Memorial rolling bascule in Toledo, OH, and the Main Street Bridge in Oshkosh, WI. Each of those projects required sequencing the deck panel replacement so the bridge stayed operable during construction, identifying weld repairs in the fatigue-sensitive locations, and providing rebalancing plans after the new deck was placed. For Miller-Sweeney, H&H will analyze the electrical and mechanical systems to determine the maximum imbalance under which the bridge can still be safely operated and will include that limit in the plans, so the contractor can develop a staged work plan against a defined criterion.

H&H's earlier inspection and remote-control study work on Miller-Sweeney provides the team familiarity with the bridge. H&H is also currently working with Caltrans on the three double leaf Strauss bascule bridges in the Sacramento region (Isleton, Paintersville, and Steamboat Slough) and recently completed a BPMP project in San Joaquin County. H&H's Caltrans process knowledge and Coast Guard coordination relationships in this region are current. Recent deck rehab experience on this type of bridge, prior hands-on knowledge of Miller-Sweeney, and active movable bridge work in the region are what H&H brings to delivering a successful project.

Miller-Sweeney is the County’s fastest movable bridge; after securing the bridge for an opening it takes 66 seconds to raise the bridge to a height of 79 degrees, a full opening. Power is supplied by two 75 hp electric motors. These motors operate in tandem for a normal opening. However, each motor can operate the bridge on its own if necessary. The backup emergency motor is a 5 HP motor. Using the emergency drive, it takes almost 20 minutes to raise the bridge to a full height.

Main power to Miller-Sweeney is supplied by the City of Alameda Bureau of Electricity and can run the bridge under normal operating conditions. An auxiliary operating panel is located on the Alameda Side of the bridge and is also powered by the Bureau of Electricity. The bridge is equipped with an emergency drives system capable of operating the bridge at a reduced speed powered by a portable 50 kW generator.

The bridge utilizes fail-safe hydraulic thruster drum brakes, two (2) motor brakes and (2) machinery brakes. The motor brakes can stop and hold the bridge in all operational positions.  The machinery brakes are larger assemblies, located adjacent to the secondary gear reduction, that provide additional brake capacity and can set to hold the bascule span for extended periods in an open position. It is our understanding that the goal of the project is to rehabilitate the existing bridge deck per the recommendations of the latest Caltrans Bridge Inspection Report (BIRIS). Along with methacrylate deck treatment of the deck, the Caltrans BIRIS recommends repairing cracks in welds connecting the web of a girder, The deck rehabilitation is estimated to extend the life of bridge deck approximately 30 years.

Deck rehabilitation will require removal of existing traffic striping, approach asphalt concrete pavement as necessary, and epoxy overlay (either complete removal or partial removal depending on repair procedure). The deck will be rehabilitated by replacing localized unsound concrete and placing methacrylate deck treatment, or approved alternative developed by H&H, for crack sealing on the fixed bridge approaches, and repair of the epoxy overlay (either full replacement or isolated repairs) on the bascule span. Approach asphalt concrete will be replaced to the extent necessary to correct sudden grade changes at bridge deck interface. Our understanding is that deck repair work on the movable span may increase the self-weight of the bridge, which could impact operations of bascule bridge.

H&H, as a subconsultant to Alaco Engineering, will perform balance testing to evaluate the current lift span balance condition. The purpose of the testing is to determine the initial balance condition. This will be done by using the dynamic strain gauging technique. While performing testing, a cursory verification of the counterweight inventory will be performed to verify adequate space for future counterweight adjustments.  Access covers and hatches will be removed by others. This effort will focus primarily on the filled/free volume at each counterweight and the type of counterweight adjustment block located is the accessible portion of the counterweight pockets.

H&H will evaluate the initial span balance test results as well as the counterweight adjustment pocket inventory findings and develop a summary memo.  The memo will contain an executive summary, strain gage testing methodology, strain gage testing results, counterweight inventory findings, and conclusions that consists of a discussion of probable error and additional recommendations determined necessary following the testing.

Given the anticipated increase of superstructure deadload, an evaluation of the span support trunnion assemblies will be performed as well as determination of operational impact to the electro-mechanical operating machinery and bridge balance.  Additional consideration of the south inboard counterweight strut with noted deficiencies will be investigated and evaluated as part of the effort.   Repair of cracked welds, such as the web of Girder 4 in Cell 3 of Span 3 to the bottom flange will be included in the work .

In addition to the bridge deck rehabilitation, our understanding is that the County is requesting for a future maintenance schedule/program to be developed with approximate cost to maintain the bridge deck to minimize further deterioration and maximize the life of the bridge deck.  H&H brings unique experience having developed movable bridge maintenance programs and manuals for numerous agencies, including Caltrans.  Our team will work with the County to establish maintenance and inspection practices to suit the County needs, that promote service life and reliability of the bridge deck.

The rehabilitation will require careful coordination of marine and vehicular traffic impacts as well as environmental impacts. We are anticipating the need for temporary lane closures or complete detour. Either Alaco Engineering or Sanbell, will provide the traffic control requirements and contract documents, including bridge closure during construction and traffic striping after the completion of deck rehabilitation. Sanbell will also assist with right-of-way mapping and base mapping for design phase. Field Surveys topographical surveys are anticipated for this project.

Drawing from our experience on the recent Caltrans and the San Joaquin BPMP project, we understand the importance of establishing acceptable marine outage windows early in design. We will coordinate with the U.S. Coast Guard to determine allowable closure periods that balance construction efficiency with maritime commerce needs. Defining these windows during design lets us develop specifications that clearly communicate time constraints to bidders, resulting in more accurate bids and realistic schedules.

We will also analyze the electrical and mechanical systems to determine the maximum imbalance condition under which the bridge can be safely operated during construction. This threshold will be included in the plans so the contractor can develop a deck replacement work plan that keeps the bridge operable through staged construction. Where possible, structural and mechanical work will be staged during approved marine outage periods to maximize productivity while the bridge is inoperable, while work that can proceed with the bridge in service, such as repairs accessible from a barge, will be scheduled to preserve navigation. Deck replacement staging limits will be coordinated with the traffic control plans developed by Alaco Engineering or Sanbell.

We are not anticipating any coordination with the utility agencies as the utilities will not be obstructed during the construction.

We have assumed that environmental (NEPA and CEQA) clearances and permits from regulatory agencies for the construction will be separately coordinated internally by the County and have not included obtaining environmental clearances and permits in our scope of work.

# SCOPE OF WORK

PHASE I: PRELIMINARY ENGINEERING (NTP [June 1, 2026] to August 31, 2026)

Preliminary Studies:

H&H will perform preliminary investigations to obtain the information of the existing conditions.

Task 1.1 – Project Administration, Project Management, and Coordination Review/Meetings H&H will perform project administration and project management, including invoicing and billing. Also, H&H will attend up to 4 coordination review meetings with the County.

### Task 1.2 – Data Collection and Site Review:

H&H will assess available information on the project, including existing drawings, As-built drawings and Caltrans Bridge Inspection (BIRIS) Reports. H&H will perform a site visit to review the condition of the structure to confirm the work requested by the County.

H&H will perform balance testing & counterweight inventory.

H&H will coordinate with the County for additional survey requests, as required.

DELIVERABLES: None

### Task 1.3 – Preliminary Investigations Right of Way Mapping and Field Survey:

H&H will coordinate with the County to determine mechanical and electrical requirements for the operation of the bridge. H&H will also coordinate with the County to obtain right-of-way maps and perform field topographical survey to prepare record database.

### Key Assumptions:

- County will provide right-of-way maps and utility maps if available

- County will provide access to counterweight pockets

## DELIVERABLES:

- Initial balance report & evaluation of available adjustment

PHASE 2: FINAL DESIGN (September 1, 2026 to Construction Bidding phase)

Based on the information available and existing bridge data, construction documents will be developed during the Final Design phase.

H&H will execute Final Design including design calculations, preparing bid plans, specifications, and estimates (PS&E) submittals. The Construction Documents package will include technical specifications and plans and details which will conform to the County Standards. Final design calculations and a construction cost estimate will be prepared and submitted for County staff's review.

The plan sheets will be prepared in AutoCAD per the County drafting standards. Plans will be prepared in English units at an appropriate scale such that plans are legible and will be consistent with the County' Standard Plans.

The bid schedule including the quantities will be provided as part of the specifications.

Technical Specifications (Special Provisions) for the specific items of work included in the construction documents will be edited to suit the project using Caltrans Standard Special Provisions 2025 and will reference the Caltrans Standard Specifications 2025. Technical structural specifications will be provided in Microsoft Word format and to be incorporated into the project special provisions by others.

A draft bridge deck maintenance program indicating deck maintenance service requirements and schedule will be developed. The approximate costs of services will be estimated to help the County with budgeting for these maintenance service costs.

## TASK 2.1: 70% DRAFT PLANS AND SPECIFICATIONS (UNCHECKED DESIGN):

70% PSCE Submittal (Unchecked): Subsequent to the preliminary rehabilitation design completed during Preliminary Engineering phase, H&H will prepare the 70% Design PS&E Submittal for review and approval by the County. The submittal will incorporate any review comments from the previous submittal by the County staff as well as those of all other reviewing agencies. The submittal will include 70% structural calculations, construction plan sheets, detail, and specifications, and 70% engineer’s structural cost estimate.

The 70% PS&E is anticipated to be completed and submitted by November 30, 2026.

## DELIVERABLES:

- Design Calculations

- Draft (Unchecked) Structural PS&E

## TASK 2.2: 100% FINAL PLANS AND SPECIFICATIONS (CHECKED DESIGN):

Quality Assurance In-house Design Check: H&H will conduct an internal quality assurance review of the design calculations, plans, specifications, and estimate as well as the bridge maintenance program; concurrent with review of County comments on the 70% PS&E submittal. H&H’s quality assurance review will include interdisciplinary coordination review to ensure consistency between the structural design and the other design documents. H&H’s quality assurance program will provide for independent checking of individual tasks, as well as an independent review by experienced senior staff lead by an Engineering Manager or higher level. The purpose of this review is to provide oversight to specific project details by professionals who are not closely involved in the design, and to review the constructability, cost-effectiveness and completeness of design features relative to the normal standard of professional care.

Design review comments from the internal quality assurance review along with the County’s review

will be resolved and incorporated into the 100% Final PS&E.

100% Final PS&E (Bid Documents) Submittal: After the County review of the 70% PS&E Submittal, H&H will prepare the Final Contract Documents by incorporating any minor final revisions and in accordance with the County ’s instructions. Submit final bid documents for signature.

100% Final PS&E is anticipated to be completed and submitted by January 31, 2027.

## DELIVERABLES:

- Design Review Comment Response Summary Form

- Final Structural PS&E

## PHASE 3: CONSTRUCTION SUPPORT SERVICES

During the construction phase of the project, H&H will provide the construction support services as listed below:

Task 3.1 	Respond to contractor bid inquiries (see hourly breakdown for hours assumed). Task 3.2 	Review Shop Drawings and Contractor Submittals – Maximum 4 total

Task 3.3 	Addressing Construction RFIs – Maximum 2 total

Task 3.4 	Preparing Change Contractor Change Order (CCOs) Task 3.5 	Review Record Drawings

Task 3.6 	Structural Observation Services – Maximum 2 total

Two site visits during construction are anticipated under this task. The first visit will occur during the initial marine outage for deck replacement on the movable span to observe the contractor's staging, removal, and installation methods, and to verify conformance with the contract documents at a critical construction milestone. The second visit will occur near project completion to observe the contractor's final span balancing and adjustments, and to confirm the bridge is ready for acceptance.